## Andres Tasks
Andrés' Unlock Data Analysis TO DO
No. | Task | Reason | Date task was set | Done? | Comments
-1 | Collect data | To have data | 2013-11-20 | Yes | Need to standarized recordings. Help in debugging and makes more productive the sessions.
0 | Load files | To be able to play with data | 2013-12-07 | Yes
1 | Create cap configuration layout to plot channels in proper location | Proper presentation of results | 2013-12-07 | No
2 | Parse data per trial | For time and frequency domain analysis and for decoding | 2013-12-07 | Yes
3 | Average data per trials | Increase SNR | 2013-12-07 | Yes
4 | Moving window to parse trials | Test how synchronized | 2013-12-15 | Yes
5 | Spectrum | Test Harmic-Sum-Decision | 2013-12-15 | Yes
6 | Spectrogram | Test synch of signal and changes in peak frequencies | 2013-12-07 | Yes
7 | Plot time and spectrogram together |  | 2013-12-15 | No | Yes partially. A problem with aligning the spectrogram and the toime domain data
8 | Get online decoder performance | Check how good current decoder is | 2014-01-01 | Yes
9 | Test new decoders to improve performance | Need to improve decoding since current approach is pretty crappy | 2013-12-15 | No | Need to subtract baseline!! Checl also log and z-scoring
10 | Define a metric (or two) for comparing photodiode results [Unlock] | To keep track of proper stimulation frequencies | 2014-01-07 | Yes | Done
11 | Define a metric or two functions to compare performance of trials [Unlock] | To compare decoder results among trials and sessions | 2014-01-07 | Yes | Done
10 or [5 5 7]
|  | vector of integers (for one block) equal to [numTrials x 1]. If more than one block, matrix of integers [numTrials x numBlock] |  | [1 2 1 3 4 2 1 2 3 4] or [1 2 1 4 3; 3 2 1 3 2; 4 1 2 3 4 2 3]
|  | vector of integers (for one block) equal to [numTrials x 1]. If more than one block, matrix of integers [numTrials x numBlock] |  | [1 2 1 3 4 2 1 2 3 4] or [1 2 1 4 3; 3 2 1 3 2; 4 1 2 3 4 2 3]
string

## Unlock Data Structure
[unlockParams] = setUnlockParams |  |  | [unlockParams] = setUnlockDefaultParams
No. | Task |  |  | Example | Function
1 | Refer to Unlock Data Structure.xls file
Sample space refers to the number of samples. The first data point is sample one. All calculation are based on samples to facilitate finding them and avoid multiplying by sampling frequency and possibly loosing precision when rounding numbers
No. | Name of variable | Type of datum | Comments | Example | Function

## iteration 3
Iteration 3 | Priority | Estimate (days) | Notes | Dependencies | Actual (days) | Status Legend
Incomplete
Andres |  | 15 |  |  |  | Unverified
Describe correct Photodiode generation | 1 | 0.25 |  |  |  | Verified
Help Dante and James to setup and collect photodiode data from unlock | 1 | 0.25 |  |  |  | Unbudgeted
Quarterback | 1 | 14 | You're the visionary scientist. We're the artisan builders. Aye Aye Captain.
Test EEG BCI Software 12/13 | 1 | 0.25 | Friday the 13th
Test EMG software | 1 | 0.25 | Not estimated to be read until the week of the 16th | Hardware Cara's lab
Test EEG BCI Software 12/20 | 1
James |  | 28.25
Collect data for Giang | 1 | 0.25
Work with The Quarterback to verify SSVEP | 2 | 3
Work with The Quarterback to verify EMG | 3 | 3
Basic recording system | 4 | 5
And another VEP-based | 5 | 4 | Work with Andres to understand
Create tutorial and documentation | 6 | 10 | Will connect with Byron for consulting; he's the only custom of our developer modality. This system has 2 types of users; users, in the conventional sense; users that rely on the infrastructure to create new things.
Break up device wrappers into separate dlls | 7 | 2 | Role over from last sprint; low priority
Push all config data to json | 8 | 1 | Role over from last sprint; low priority
Giang |  | 6.75
Test current code with data from NPL | 1 | 2
Setup Skype meeting where we can discuss our idea with The Quarterback (Andres) to ensure we are building the right stuff. | 2 | 0.25
Write spectrogram code | 3 | 2
Test spectrogram code with real data and simulated data | 4 | 2
Dante |  | 0.25
Help Andres and James collect photodiode data for Giang. | 1 | 0.25
? | 0 | ? | Dante expressed possible interest in getting a project, which would be very positive. I have a few juicy resume bullet type ones that need to be done.
Backlog
|  | Decoding online learning (selection window frequencey) | Use online learning techniques to update classifiers in real-time
|  | Drop outliers during decoding | Intelligently detect and ignore outlier values.
|  | Decoding signal quality awareness | Monitor and account for signal quality issues during decoding
|  | Continous Calibrate | Apply online techniques to continuous calibration
|  | Analysis platform | This would include a lot of the tools necessary to do decoding research.
|  | Diagnostics | Expand upon frequency scope app; basically equivalent to the NIC
|  | Admin | Build an admin website
|  | EC2 Server | This is an AWS server to host the Unlock content.
|  | EEG Lab (matlab clone) | Mimic MATLab setup
|  | BCI Lab (matlab clone) | Mimic MATLab setup
|  | Emotiv | Hardware support
|  | USBAmp | Hardware support
|  | NeuroSky? | Hardware support
|  | Audio EMG interface | Hardware support
|  | Extend DAQ support | Hardware support
|  | Laser BOT | Hardware support
|  | Sweep APP | App support
|  | Sk-learn based classifier support | Use standard machine learning platform for Python
|  | BCI DSL | Byron and I discussed a language that could be used to describe BCI based applications. I think this is a great idea, but it needs a bit of work.
|  | Persistent state for Apps | Currently if not all the dependent packages are installed the system will fail to start. This means the DAQ driver software, enobio and mobilab today. This list could grow over time and should be decoupled as it is with the OS. Only the software you need will be loaded.
MVC
View chaining
Model chaining
Model state change dispatching
Documentation
Python doc string annotations
Sphinx API documentation website
Github wiki page (features, install)
Tutorial
Video
Differing channel weights [equal channel weights]
---Canonical Correlation Analysis---[backlog] Implement from paper and evaluate
---Adaptive Filter Bank---[backlog] Implement from paper and evaluate
Differing harmonic weights [equal harmonic weights]
Baseline referencing [no baseline comparison]
Baseline referencing [no baseline comparison]
Differing frequency windows [2 bins centered on each target frequency]
Differing FFT resolutions [nfft = 2048]
Differing time windows [t = 3s]
Differing PSD estimators [fft] - Periodogram - Multi-taper - WaveletInvestigate P_episode, an oscillatory event detector in the time domain [4]

## Contact List
Unlock Contact List
No. | Group Leader (G.P.) | G.P. Leader Email | Contact | Contact Email | Type of studies
1 | Frank Guenther |  | Andrés Salazar | salacho@bu.edu | Steady-state visually evoked potentials (SSVEP)
2 | Barbara. Shinn Cunningham |  | Lenny |  | Steady-state auditory evoked potentials (SSAEP)

## Applications
Applications
No. | Application Name | Proposed by | Short Description
1 | SSVEP-based speller | Frank Guenther
2 | SSVEP-based TV remote control
3 | SSVEP-based roomba control
4 | SSAEP-based